## I-200 Project Plan
Template Project Plan 2023 - 2024
ID | MM/DD/YYYY | Duration | Start | End | Predecessors | %Complete | Resource Name | Comments
Initiation
Create Project Structure
Identify Key Stakeholders
Identify Subject Matter Experts (SMEs)
Identify funding source
Create meeting schedule
Define Project Team and Structure
Planning
Schedule a kickoff Meeting
Official project kick-off
Identify project Steering Committee
Define roles and responsibilities and obtain buy-in
Schedule a Steering Committee Meeting
Schedule Kick-off meeting with the project team
Meet with End user(s) discuss requirements, walk the location if necessary
Provide insight into student’s use of the facility as a space for learning
Solicit design ideas for the space
Develop Requirements/Specifications
Draft of the floor plan/Design
Identify External Contractors
Identify Internal Participants
Design Approval
Furniture Vendor walkthrough
Meet and discuss the space with vendors
Solicit actual design plan ideas from vendors
Get feedback from the faculty
Equipment, software and layout and design idea
Get feed back from the students (type of equipment, software and layout and design idea)
Survey to gather data from students went out to the Office of Institutional Effectiveness to be approved
Survey to go out to the students
Finalize the Space layout and structure
Based on the space’s proposed utilization, provide feedback on the proposed furniture and layout
Obtain 2-3 ideas for final layout
Bring ideas to Steering Committee for approval
Obtain a voted upon approval from the steering committee
Executing
Flooring Development and Procurement
Discuss with the project team
Create requirement document
Procurement Management
Conduct Bid
Select Vendor
Review the quotes with the SMEs
Process Quotes
Submit the quote into RTS
Budget line gets approved
Follow up with ITS Budget and Finance
Purchase ID gets created
Follow up with Purchasing
Purchase Order gets created
Vendor receives Purchase Order
Vendor fullfills Purchase Order
Vendor ships materials to QC
Receipt of material
Installation
Vendor Management
Submit Receiving Reports into RTS
Ceiling Tiles
Discuss with the project team
Procurement Management
Conduct Bid
Select Vendor
Process Quotes
Review the quotes with the SMEs
Submit the quote into RTS
Budget line gets approved
Follow up with ITS Budget and Finance
Purchase ID gets created
Follow up with Purchasing
Purchase Order gets created
Vendor receives Purchase Order
Vendor fullfills Purchase Order
Vendor ships materials to QC
Receipt of material
Installation
Vendor Management
Submit Receiving Reports into RTS
Partition
Discuss with the project team
Create requirement document
Procurement Management
Conduct Bid
Select Vendor
Process Quotes
Review Quotes
Submit into RTS
Purch. req. processing
PO processing
Follow up with Purchasing
Purchase Order gets created
Vendor receives Purchase Order
Vendor fullfills Purchase Order
Vendor ships materials to QC
Receipt of material
Installation
Vendor Management
Submit Receiving Reports into RTS
Electrical
Discuss with the project team
Create requirement document
Create Layout
Get approval of layout from Core team
Coordinate with B&G
Submit Electrical work requests to B&G
Get Materials list from B&G
Procurement Management
Process Quotes
Review Quotes
Submit into RTS
Purch. req. processing
PO processing
Follow up with Purchasing
Purchase Order gets created
Vendor receives Purchase Order
Vendor fullfills Purchase Order
Vendor ships materials to QC
Receipt of material
Coordinate the work with B&G
Data
Discuss with the project team
Create requirement document
Create Layout
Get approval of layout from Core team
Procurement Management
Process Quotes
Review Quotes
Submit into RTS
Purch. req. processing
PO processing
Follow up with Purchasing
Purchase Order gets created
Vendor receives Purchase Order
Vendor fullfills Purchase Order
Vendor ships materials to QC
Receipt of material
Coordinate the work with Telecommunication Group
Lighting
Discuss with the project team
Procurement Management
Process Quotes
Review Quotes
Submit into RTS
Purch. req. processing
PO processing
Purchase Order gets created
Vendor receives Purchase Order
Vendor fullfills Purchase Order
Vendor ships materials to QC
Receipt of material
Follow up with Purchasing
Coordinate the work with B&G
HVAC
Coordinate with B&G
Submit HVAC work requests to B&G
Coordinate the work with B&G
Paint
Discuss with the project team
Create requirement document
Create Layout
Get approval of layout from Core team
Procurement Management
Process Quotes
Review Quotes
Submit into RTS
Purch. req. processing
PO processing
Follow up with Purchasing
Purchase Order gets created
Vendor receives Purchase Order
Vendor fullfills Purchase Order
Vendor ships materials to QC
Receipt of material
Coordinate the work with B&G
Shades
Procurement Management
Process Quotes
Review Quotes
Submit into RTS
Purch. req. processing
PO processing
Follow up with Purchasing
Purchase Order gets created
Vendor receives Purchase Order
Vendor fullfills Purchase Order
Vendor ships materials to QC
Receipt of material
Installation
Facilities Items Purchasing Milestone
Furniture
Coordinate with Facilities
Furniture
Standing height work surfaces with no chairs - Look into and advise
Get specs for the furniture
Discuss with the project team
Create requirement document
Create Layout
Get approval of layout from Core team
Procurement Management
Process Quotes
Get quotes
Review the quotes with the SMEs
Submit the quotes into RTS
Budget line gets approved
Follow up with ITS Budget and Finance
Purchase ID gets created
Follow up with Purchasing
Purchase Order gets created
Purchasing Furniture Milestone
Technology
Audio-Visual
Provide design proposals for audio-visual technology
Review and approve Design proposal
Provide quotes for audio-visual technology
Procurement Management
Process Quotes
Get quotes
Review the quotes with the SMEs
Submit the quotes into RTS
Budget line gets approved
Follow up with ITS Budget and Finance
Purchase ID gets created
Follow up with Purchasing
Purchase Order gets created
Vendor receives Purchase Order
Vendor fullfills Purchase Order
Vendor ships materials to QC
Receipt of material
Installation
Configure and Test
Gaming Devices
Provide design proposals for gaming technology
Review and approve Design proposal
Provide quotes for gaming technology
Procurement Management
Process Quotes
Review Quotes
Submit into RTS
Budget line gets approved
Follow up with ITS Budget and Finance
Purchase ID gets created
Follow up with Purchasing
Purchase Order gets created
Vendor receives Purchase Order
Vendor fullfills Purchase Order
Vendor ships materials to QC
Receipt of material
Installation
Configure and Test
Security Cameras
Provide design proposals for security technology
Review and approve Design proposal
Provide quotes for security technology
Procurement Management
Process Quotes
Review Quotes
Submit into RTS
Budget line gets approved
Follow up with ITS Budget and Finance
Purchase ID gets created
Follow up with Purchasing
Purchase Order gets created
Vendor receives Purchase Order
Vendor fullfills Purchase Order
Vendor ships materials to QC
Receipt of material
Installation
Configure and Test
Phone
Coordinate with Telephone Services
Charging/Loan Lockers - Phase 2
Provide information about charging/loan locker technology available
Provide design proposals for charge/loan lockers
Review and approve charge/loan lockers proposal
Get specs for the Lockers
Discuss with the project team
Create requirement document
Procurement Management
Process Quotes
Work with Purchaasing: Create RFP
Assess RFP responses
Review RFP responeses with SMEs
Approve vendor
Submit the quotes into RTS
Budget line gets approved
Follow up with ITS Budget and Finance
Purchase ID gets created
Follow up with Purchasing
Purchase Order gets created
Budget line gets approved
Follow up with ITS Budget and Finance
Purchase ID gets created
Follow up with Purchasing
Purchase Order gets created
Vendor receives Purchase Order
Vendor fullfills Purchase Order
Vendor ships materials to QC
Receipt of material
Installation
Configure and Test
Computers and Printers - Coordinate with the Help Desk
Computers
Provide proposals for computers
Get specs for the computers
Review and approve computer proposal
Submit tickets to Fresh service
Get quotes for the computers
Review the quotes with the SMEs
Submit the quotes into RTS
Budget line gets approved
Follow up with ITS Budget and Finance
Purchase ID gets created
Follow up with Purchasing
Purchase Order gets created
Receive equipment's
Tagged the equipment
Unpack and set up
Get rid of boxes
Secure the equipment (put locks on them)
Test and configure
Submit Receiving Reports into RTS
Printers
Get specs for the printers
Review and approve printer proposal
Submit tickets to Fresh service
Get quotes for the printers
Review the quotes with the SMEs
Submit the quotes into RTS
Budget line gets approved
Follow up with ITS Budget and Finance
Purchase ID gets created
Follow up with Purchasing
Purchase Order gets created
Receive equipment's
Tagged the equipment
Unpack and set up
Get rid of boxes
Secure the equipment (put locks on them)
Test and configure
Submit Receiving Reports into RTS
Completed Procurement Processes
Vendor Management
Monitor the progress
Inspect ongoing work
Provide status reports regularly to stakeholders
Phase 1 General Contracting
Vendor management
Coordinate work dates with the vendor
Provide vendor with access to the room
Contractor completes work
Contractor clean up
QC Inspection
Submit Receiving Reports into RTS
Phase 1 Furniture Installation
Vendor management
Coordinate Installation Date (s) with the vendor
Provide vendor with access to the room
Vendor Installs Furniture
Contractor clean up
QC Inspection
Submit Receiving Reports into RTS
Milestone for Furniture installation
Closing
Punch list
Rendering of services
Knowledge and Documentation transfer
Lesson Learned
Soft Opening
Prepare the report and sign off
Sign off
Close the project
Go Live
Celebrate!!